## Sheet1
Annexure-2 BOQ
Installation of Firefighting lines in BOP and Main Plant area above ground
Sl.No | Area Segment | Hydrant & Spray | Material Description | UOM | Quantity | Unit Rate | Amount | Remarks (Completion Time)
1 | Fire Pump House to Fire Station Junction | H1 | 300 NB MS Pipe as per IS 3589 | Mtr | 375 |  |  | 60 DAYS
2 |  | H2 | 300 NB MS Pipe as per IS 3589 | Mtr | 325
3 |  | Spray | 250 NB MS Pipe as per IS 3589 | Mtr | 380
4 |  | Hydrant &Spray | 300 NB 90 deg Elbow | Nos | 18
5 |  |  | 300 NB 90 deg Elbow | Nos | 18
6 |  |  | 250 NB 90 deg Elbow | Nos | 18
7 |  |  | Structural Steel MC 150 | MT | 2.3
8 | Fire station to Silo Gate | H1 | 300NBMS Pipe as per IS 3589 | Mtr | 90 |  |  | 90 days
9 |  | H2 | 300NBMS Pipe as per IS 3589 | Mtr | 160
10 |  | H2 | 250 NBMS Pipe as per IS 3589 | Mtr | 220
11 |  | H2 | 200NB MS Pipe as per IS 3589 | Mtr | 126
12 |  | Spray | 250 NB MS Pipe as per IS 3589 | Mtr | 560
13 |  | Hydrant &Spray | 300 NB 90 deg Elbow | Nos | 6
14 |  |  | 300 NB 90 deg Elbow | Nos | 6
15 |  |  | 250 NB 90 deg Elbow | Nos | 12
16 |  |  | 200 NB 90 deg Elbow | Nos | 6
17 |  |  | Structural Steel MC 150 | MT | 4
18 | TT6 to DOT | H2 | 200 NBMS Pipe as per IS 3589 | Mtr | 375 |  |  | 45Days
19 |  | Spray | 200 NBMS Pipe as per IS 3589 | Mtr | 325
20 |  | Spray | 150NB MS Pipe as per IS 1239 | Mtr | 72
21 |  | Hydrant &Spray | 200 NB 90 deg elbow | Nos | 6
22 |  |  | 150 NB 90 deg elbow | Nos | 6
23 |  |  | Structural Steel MC 150 | MT | 1.5
Total Basic Value
GST @ 18%
Total Amount ( Basic + GST)